## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Base infrastructure & I/O (Brain + Nucleo) | Project Plan – BFMC Brain (URT) Platform: Raspberry Pi 5 / Jetson Orin Nano + STM32 NUCLEO Repo: urt-brain-bosch Current status: • Local YOLO perception + lane keeping operational • Stanley control, dashboard, serial link, and V2X modules integrated • Traffic signs, traffic lights, and parking FSM implemented Current focus: • Reliability, latency, and edge-case tuning • Final competition validation on full-track scenarios | Camera pipeline: capture, streaming, preprocessing, ROI definition | [6 empty] | Serial handler (STM32) + IMU integration + motor/steering control; system services (autostart) + Wi‑Fi fallback | [15 empty] | BFMC
Gateway + state machine: message routing, operation modes, dashboard controls, traffic/semaphore communications
[18 empty] | Robustness for lighting changes: HSV calibration, exposure checks, regression tests |  |  |  | Refactors & performance optimizations
Vision & perception |  | Lane detection (OpenCV): BEV + sliding window + centerline |  |  |  | Lane-following tuning: curves, lookahead, speed reduction on bends |  |  |  | Traffic sign detection & reactions |  |  |  | Traffic light state handling
[12 empty] | Obstacle & pedestrian handling | [5 empty] | Intersection / road-type handling
[14 empty] | YOLO local perception: classes, masks, detections |  |  |  | Detection tuning & validation
Traffic server + semaphores integration
Other optimizations
Decision making & planning |  | System architecture: processes/threads, state machine, topic routing, dashboard API | [7 empty] | Behavior planning: priorities, rules, maneuver sequencing |  |  |  | Safety & fail-safes: serial timeout, emergency stop, speed limits per context
State-driven actions: stop, crosswalk, priority, parking, lights
[18 empty] | Robustness tests: lost frames, bad masks, wrong detections, recovery strategies |  |  |  | Other functionalities
Vehicle control |  | PID steering + speed control; smoothing + limits; curve speed adaptation | [7 empty] | Intersection navigation |  |  |  | Implemented: stop, crosswalk, traffic-light response, parking |  |  |  | Next: obstacle avoidance, roundabout handling, rerouting
Other optimizations
Integration & deliverables | Demonstrate: manual control + autonomous mode, dashboard monitoring, and stable on-device services. | Stable lane keeping + local perception integrated on the vehicle | [7 empty] | Qualification-ready behavior set with core traffic-rule compliance |  |  |  | End-to-end V2X loop: traffic server + semaphore state + actions |  |  |  | Competition-ready: optimize latency, edge cases, logging, and repeatable test runs
|  | Build/maintain a physical testing track + lighting scenarios |  |  |  | Parallel development workflow: modular tests + CI checks + logging
Simulation / virtual testing environment (Gazebo or lightweight replays)
Final optimizations
Deadlines |  |  |  | 2025-12-22 |  |  |  |  | 2026-02-02 |  |  |  | 2026-03-09 |  |  |  | 2026-04-13 | [7 empty] | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20
Checkpoint |  |  |  | Status 1 | Christmas brake |  |  |  | Status 2 |  |  |  | Qualification |  |  |  | Status 3 | [7 empty] | Testing day 1 | Testing day 2 | Testing day 3 | Semi-finals | Final

## Plan_Details
Project Plan - BFMC Brain (URT)
General Information
Project | Bosch Future Mobility Challenge - Autonomous Driving Brain
Team | URT (Universidad Rafael Urdaneta)
Platform | Raspberry Pi 5 / Jetson Orin Nano + STM32 NUCLEO
Repository | urt-brain-bosch
Project Description
Summary | Autonomous driving brain for the BFMC scale vehicle, combining local YOLO perception, Stanley-based lane control, STM32 serial actuation, V2X traffic/semaphore communication, parking maneuvers, and web dashboard monitoring.
System Architecture Snapshot
Hardware components | Raspberry Pi 5 / Jetson Orin Nano (main processing) STM32 NUCLEO (motor / steering / IMU / encoder bridge) IMX219 CSI or USB camera Servo + DC motor drivetrain Onboard dashboard + traffic communication stack
Software Modules
Module | Location | Function
Main | main.py | Entry point and process orchestration
Camera | src/hardware/camera/ | Frame capture, local perception, lane following
Serial Handler | src/hardware/serialhandler/ | Serial I/O with NUCLEO and actuator commands
Gateway | src/gateway/ | Queue / pipe routing between processes
State Machine | src/statemachine/ | Mode transitions and shared system state
Dashboard | src/dashboard/ | Flask + Socket.IO backend and Angular frontend
Traffic Comm | src/data/TrafficCommunication/ | Competition traffic server communication
Semaphores | src/data/Semaphores/ | Smart traffic-light / semaphore reception
Implemented Features
Completed | • Multiprocess + multithread runtime running on the vehicle • Camera capture, local YOLO perception, and autonomous lane keeping • Stanley steering controller + speed scheduling • Serial read/write with NUCLEO (IMU, speed, steer, battery) • Dashboard backend/frontend + manual and automatic modes • Traffic sign and traffic light reactions • Parallel parking FSM and sign-action handling • Traffic communication + semaphore integration • Autostart services, logging, and calibration utilities
In progress | • Full-track robustness tuning and latency optimization • Edge-case validation for intersections, obstacles, and lighting changes • Competition-oriented testing, recovery behavior, and repeatability
Pending | • Final route-planning polish and competition-scenario validation • More regression tests and performance optimization
Project Phases
Phase | Scope | Status
Phase 1: Core Infrastructure | Main process, serial link, dashboard, state machine, services | COMPLETED
Phase 2: Local Perception & Lane Keeping | Camera capture, YOLO lanes/signs, Stanley control | COMPLETED
Phase 3: Behavior Execution | Sign actions, traffic-light response, parking FSM, safety rules | COMPLETED
Phase 4: Competition Integration | Traffic server, semaphores, end-to-end runtime robustness | IN PROGRESS
Phase 5: Final Validation | Full-track testing, optimization, edge cases, finals preparation | IN PROGRESS
Current System Parameters
Control & Lane Following
Parameter | Value | Description
max_steering | ±25° | Maximum steering command
stanley_k | 2.5 | Crosstrack gain
stanley_k_soft | 3.0 | Low-speed softening
stanley_k_d_steer | 0.10 | Steering damping
steer_history_len | 2 | Steering smoothing history
noise_max_steer_jump_deg | 15° | Maximum accepted jump before rejection
lf_min_speed | 10 | Normal minimum speed
lf_max_speed | 15 | Normal maximum speed
Local Perception
Parameter | Value | Description
model | Best_weights_reentrenado_416px.engine | Primary TensorRT model
input_size | 416 | Model input size
min_confidence | 0.35 | General detection threshold
sign_min_confidence | 0.55 | Traffic-sign threshold
Fallback / Auxiliary Modules
LSTR fallback | ONNX / OpenVINO lane detector
OpenCV fallback | HSV + Canny + Hough lane pipeline
Known Issues and Solutions
Current Reliability Notes
Issue | Cause | Solution
Lighting-sensitive scenes | Rapid illumination changes | Recheck exposure / HSV and validate masks
Sudden steering jumps | Noisy lane detections | Use noise filter + steer history smoothing
Missed signs / lights | Thresholds or crop mismatch | Tune confidence thresholds and input framing
Serial reconnection needed | USB /dev/ttyACM reset | Restart serial handler and check the cable
General System
Issue | Cause | Solution
Dashboard unavailable | Backend / frontend service down | Restart dashboard services
AI FPS drops | Heavy model or CPU fallback | Prefer TensorRT / disable extra debug windows
V2X data missing | Traffic or semaphore link offline | Check UDP/TCP connectivity and keys
Useful Commands
Start brain | cd /home/pi/Documents/urt-brain-bosch python3 main.py
Start frontend | cd src/dashboard/frontend ng serve --host 0.0.0.0
View services | journalctl -u brain-autostart -f journalctl -u angular-autostart -f
Restart services | sudo systemctl restart brain-autostart sudo systemctl restart angular-autostart
Key File Structure
Repository tree (excerpt) | urt-brain-bosch/ ├── main.py ├── config.py ├── src/ │ ├── hardware/camera/ │ ├── hardware/serialhandler/ │ ├── statemachine/ │ ├── gateway/ │ ├── dashboard/ │ └── data/ ├── models/ ├── services/ ├── tests/ └── calibration/
Change History
Date | Change | Author
2026-03-09 | Updated project plan from current architecture snapshot | -
2026-03-09 | Added YOLO perception, Stanley control, parking FSM, and V2X status | -
2026-03-09 | Updated competition milestones and event dates | -
2026-03-09 | Refreshed modules, parameters, and reliability notes | -